## Sheet1
Prototype Title: | Ride or Die (idk lol)
Scope:
Repository Link:
Class | Functionality | Description | Program | Start Phase/Week | End Phase/Week | Assigned to | Complete Y/N? | Notes
Player | Movement | basic character movement. Left/Right/Forward/Back |  | week3 |  | Devin | Y | succesfully added movement, attempted to adjust camera to allow for up/down rotation, to no avail.
Level-up
| Player UI |  |  | week3 |  | Rylan
Base stats
Do-Damage Mechanic
Take-Damage Mechanic
Pickups | Power-Up Pickup (A)
Power-Up Pickup (B)
Power-Up Pickup (C)
Power-Up Pickup (D)
Player Equipment Pickup(A)
Player Equipment Pickup(B)
Player Equipment Pickup(C)
Player Equipment Pickup(D)
Enemies (Basic) | AI Movement |  |  | week3 |  | Travis
Base stats
| Do-Damage Mechanic |  |  | Week3 |  | travis
Take-Damage Mechanic
Enemies (Empowered) | AI Movement
Base stats
Do-Damage Mechanic
Take-Damage Mechanic
Map & Map Features | Obsticles (A) |  |  | week3 |  | Kenan
Obsticles (B)
Obsticles (C)
Obsticles (D)
| Base Map |  |  |  |  | Zach
| Test Environment |  |  | week 3 |  | Zach